## Iteration 1
CS Capstone Task Tracker It. 1
Real Time Network Visualization Team
T-# | Tasks | Due Date | Distribution Info | Status | Remarks | Key
1 | XML Documentation | 22–Mar–10 | Full Team | Complete | XML Format for Front end team | Not Started | Stop
2 | Software Installation | 24–Mar–10 | Full Team | Complete | Installation of Snort, tcpdump, etc | In Progress | Working
3 | Simple Log Parsing | 25–Mar–10 | Lockwood, King | Working | Pull Ips, simple attack tags from logs | Complete | Complete
4 | XML outputting | 2010-03-26 | Jackson | Complete | Convert Parse output to XML | On-Hold | Standby
5 | Documentation | 2010-03-26 | King | Complete | Compile SRS info, pamphlet form

## Iteration 2
CS Capstone Task Tracker It. 2
Real Time Network Visualization Team
T-# | Tasks | Due Date | Distribution Info | Status | Remarks | Key
1 | XML Documentation, Node detection | 2010-03-29 | King | Complete | Establish XML format, send to front-end and Daniel Sawyer | Not Started | Stop
2 | Traffic Monitor - Manipulating Snort Rules | 2010-03-30 | Rollins, Lockwood | Complete | Learn how to add/modify Snort rules and what it picks up by default | In Progress | Working
3 | Node detection - Input config | 2010-03-30 | King | Complete | Complete Config file and IP address input | Complete | Complete
4 | XML Generation, Node detection | 2010-03-31 | Jackson | Complete | Generate XML from my Node detection output | On-Hold | Standby
5 | Node detection - Basic Complete | 2010-04-02 | King | Working | 1st Revision of Node detection, should have all basic functionality
6 | Traffic Monitor - 1st Revision | 2010-04-02 | Rollins, Lockwood | Working | 1st Revision of Traffic Monitor, parse snort logs, generate needed output, basic attack types

## Iteration 3
CS Capstone Task Tracker It. 3
Real Time Network Visualization Team
T-# | Tasks | Due Date | Distribution Info | Status | Remarks | Key
1 | Testing Node detection on router | 2010-04-07 | King | Complete | Need to get access to router to test node detection | Not Started | Stop
2 | Test pingsweeping vs. ARP cache | 2010-04-07 | King | Complete | Check time of pingsweeping for active node detection | In Progress | Working
3 | Stat tracking tools | 2010-04-07 | Rollins | Complete | Establish method to be used for stat tracking | Complete | Complete
4 | Attack Detection XML fix | 2010-04-07 | Jackson, Lockwood | Complete | Fix the XML generator for Attack Detection to reflect the full output of the program | On-Hold | Standby
5 | Debugging node Detection | 2010-04-09 | King | Complete | Fix bugs in node detection. Correct problems in bash coding.
6 | Research new rules for attack detection | 2010-04-09 | Lockwood | Complete | Find ways to track new attack types
7 | Stat tracking crude implementation | 2010-04-09 | Rollins | Complete | Get a basic stat tracking system running
8 | SRS update | 2010-04-09 | Jackson, King | Complete | Bring SRS up to date

## Iteration 4
CS Capstone Task Tracker It. 4
Real Time Network Visualization Team
T-# | Tasks | Due Date | Distribution Info | Status | Remarks | Key
1 | Node Detection – Add Caching | 2010-04-12 | King | Complete | Rough Implementation of OS Caching | Not Started | Stop
2 | Generate Logfiles | 2010-04-13 | Extras | Complete | Generate snort log files for Lockwood | In Progress | Working
3 | Installation on router | 2010-04-13 | King, Lockwood, Sawyer | Complete | Install and configure software on new router | Complete | Complete
4 | Prepare Production Test | 2010-04-14 | All team | Complete | Fix bugs, implement automation, prepare Production test for review in class 4/9 | On-Hold | Standby
5 | Review Production Test Results | 2010-04-16 | King | Working | Review results of Production test for completeness and prepare revisions and fixes for team
6 | Bug fixes for next Review | 2010-04-19 | All team | Working | Make changes and fix bugs to push a final revision
7 | Develop new rules for Snort | 2010-04-16 | Lockwood, Extras | Working | Using new logfiles, develop more rules for attack detection